## Sheet1
| Sr no. | Tasks | Expected outcome | Ideal Completion date | Actual Completion Date | Comments
| 1 | MSTR Setup & Questionnaire |  | 2023-07-20 | 2023-07-20
| 2 | Schema & Application objects |  | 2023-07-21 | 2023-07-21 |  |  |  | Legend
| 3 | Dataset |  | 2023-07-22 | 2023-07-22 |  |  |  |  | Completed
| 4 | Dashboard |  | 2023-07-24 | 2023-07-24 |  |  |  |  | In progress
| 5 | Documentations |  | 2023-07-25 | 2023-07-25 |  |  |  |  | Not started
6
7
Task breakdown | 20th July |  | 21st July |  | 24th July |  | 25th July
| 1st half | 2nd half | 1st half | 2nd half | 1st half | 2nd half | 1st half | 2nd half
Data Analysis (High level) + SQL
Requirement Questionnaire
MSTR and Project Setup
Data Modelling & Schema creation
Objects & Dataset Development
Dashboard Development
Total Formatting
Testing (Data, Func and UI)
Presentation & Documentations